## Sheet1
[8 empty] | Ian Crotty | Updates
[8 empty] | 2012-10-23 | 2012-10-31
Production and Testing of QC HV Cables
Required Labels to be applied.
[8 empty] | Imtiaz Labels |  | Pin ID or length ID | Date Voltage applied
Destination | Number | Quantity | Connector | Quantity | Connector | Quantity | Length |  |  |  |  | Test | Breakdown
[7 empty] | [m] | Serial # | Serial # |  | [15kV] | [ok or Not ok] | notes
904 QC4-1 |  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 12
| 1 | [5 empty] | 12 | 001 | 001 | Pin ok | 2012-10-19 | ok
| 2 | [5 empty] | 12 |  | 002 | Pin ok | 2012-10-22 | no | 1mA @ 2384V outer pin
| 3 | [5 empty] | 12 |  | 003
| 4 | [5 empty] | 12 |  | 004
| 5 | [5 empty] | 12 |  | 005
| 6 | [5 empty] | 12 |  | 006
904 QC4-2 |  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 11
| 1 | [5 empty] | 11 | 001 | 007 | Pin ok | 2012-10-17 | ok
| 2 | [5 empty] | 11 | 002 | 008 | Pin ok | 2012-10-17 | ok
| 3 | [5 empty] | 11 | 003 | 009 | Pin ok | 2012-10-22 | ok
| 4 | [5 empty] | 11 | 004 | 010 | Pin ok | 2012-10-19 | ? | 0.1µA @ 15kV outer pin
| 5 |  |  |  | Cable marked 1m |  | 11? | 005? | 011 | Pin ok | 2012-10-22 | ? | 0.1µA @ 15kV outer pin
| 6 | [5 empty] | 11 | 006 | 012 | Pin ok | 2012-10-19 | ok
|  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 12
| 1 | [5 empty] | 12 |  | 013 |  |  |  | Ambiguous number scheme
| 2 | [5 empty] | 12 |  | 014 |  |  |  | Ambiguous number scheme
| 3 | [5 empty] | 12 |  | 015 |  |  |  | Ambiguous number scheme
| 4 | [5 empty] | 12 |  | 016 |  |  |  | Ambiguous number scheme
| 5 | [5 empty] | 12 |  | 017 |  |  |  | Ambiguous number scheme
| 6 | [5 empty] | 12 |  | 018 |  |  |  | Ambiguous number scheme
|  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 13
| 1 | [5 empty] | 13 |  | 019
| 2 | [5 empty] | 13 |  | 020
| 3 | [5 empty] | 13 |  | 021
| 4 | [5 empty] | 13 |  | 022
| 5 | [5 empty] | 13 |  | 023
| 6 | [5 empty] | 13 |  | 024
|  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 14
| 1 | [5 empty] | 14 | 001 | 025 | Pin ok | 2012-10-22 | no | BD 0.1µA @ 15kV centre pin
| 2 | [5 empty] | 14 | 002 | 026 | Pin ok | 2012-10-19 | ok
| 3 | [5 empty] | 14 | 003 | 027 | Pin ok | 2012-10-19 | no | only one BD (break down)
| 4 | [5 empty] | 14 | 004 | 028 | Pin ok | 2012-10-22 | ok
| 5 | [5 empty] | 14 | 005 | 029 | Pin ok | 2012-10-19 | no | 1mA @ 2kv outer pin BD once
| 6 | [5 empty] | 14 | 006 | 030 | Pin ok | 2012-10-22 | ok
Spares |  | 2 | 3 Pole female | 1 | Jupiter Female | 2 | 12
| 1 | [5 empty] | 12 |  | 031
| 2 | [5 empty] | 12 |  | 032
Lalit |  | 4 | 3 Pole female | 1 | Jupiter Female | 2 | 10
| 1 | [5 empty] | 10 | 001 | 033 | no length | 2012-10-17 | ok
| 2 | [5 empty] | 10 | 002 | 034 | no length | 2012-10-17 | ok
| 3 | [5 empty] | 10 | 003 | 035 | no length | 2012-10-17 | ok
| 4 | [5 empty] | 10 | No number | 036 | no length | 2012-10-17 | ok
no Pin ID
Belgium QC3 |  | 6 | 3 Pole female | 1 | Jupiter Female | 2 | 13
| 1 | [5 empty] | 13 |  | 037
| 2 | [5 empty] | 13 |  | 038
| 3 | [5 empty] | 13 |  | 039
| 4 | [5 empty] | 13 |  | 040
| 5 | [5 empty] | 13 |  | 041
| 6 | [5 empty] | 13 |  | 042
904 Prod |  | ? |  |  |  |  | ?
| 1 | [7 empty] | 044
| 2 | [7 empty] | 045
| ? | [7 empty] | 046