## Slide 1
Waqar Ahmed
National Centre for Physics-Islamabad
HV/LV Power System
&
On board electronics

## Slide 2
High Voltage (HV) and Low Voltage (LV) is required to power up 144 RPCs which will be installed on RE+4 and RE-4.
The same solution from CAEN, Italy i.e. EASY3000 (Embedded Assembly SYstem) will be used for RE4 HV and LV system.
  To save cost for HV boards, HV distributor boxes will be produced locally as it was done previously for RE1, RE2 and RE3.
Introduction

## Slide 3
S.no | Components | Current Status | Estimated Delivery
1. | FEB (1st batch shipment, 200 Boards) | Completed | 
2. | FEB (Final Shipment, 450 Boards) |  | 1st week of August
3. | DB (1st batch shipment,100 Boards) | Completed | 
4. | DB (Final batch shipment, 150 Boards) |  | 1st week of August
5. | Coaxial cable with adapter (1st batch shipment, 40 Chambers) | Completed | 
6. | Coaxial cable with adapter (Final batch shipment, 160 Chambers) | Completed | 
FEB/DB/Coaxial cable with Adapter
Current status
The total requirement of 200 Chambers
  FEB = 600 with 10% contingency
  DB = 200 with 10% contingency
  Coaxial cable with adapter Boards= 200

## Slide 4
Cabling Current Status
S.No | Components | Current Status | Expected delivery | Remarks
1. | HV cables RE+4 | Tested in 904 | Completed | P5-installation
2. | HV cables RE-4 |  | 1st week of August | 
3. | LV cable RE+4 | Patch panel connector pending | Completed | P5
4. | LV cable RE-4 |  | 1st week of August | 
5. | Signal cable RE+4 | Tested in 904 | Completed | P5-Installation
6. | Signal cable RE-4 | Tested in 904 | Completed | 904 (1 damage,2 increase length)
7. | DCS cable RE+4 | Tested in 904 | Completed | P5- Installation
8. | DCS cable RE-4 | Tested in 904 | Completed | 904

## Slide 5
H.V Module Current Status
S.no | Components | Requirement | Expected Delivery
1. | SY1527 | not required | 
2. | EASY Crate | not required | 
3. | HV Board A3512N (6 Channel Board) and 3 HV boards per rack in USC | 12 +2 | September
4. | A3485(3-phase 400 Vac . 48 Vdc (2 ch x 2.5 kW) Converter) | 1 | September
5. | Branch Controller | not required | 
6. | HV Distributor Box (20 input 55 output) | 8 + 4 | September

## Slide 6
L.V Module Current Status
S.no | Components | Requirement | Status | Expected delivery | Remarks
1. | SY1527 | not required |  |  | 
2. | EASY Crate | 4 | 2 | September | 
3. | LV Board A3009 (12 Channel Board) | 12 | 5 | September | 
4. | MAO (A3486/A3486S) | 2 |  | September | 
5. | Branch Controller | 2 | 4 |  | Completed

## Slide 7
H.V distributor will be prepare with new scheme and new method, develop easily 1-4, 1-2 and 1-1 circuit combination with less components(white blocker, ring , ground cable and less sty-cast and glass box).
H.V Distributor

## Slide 8
HV Module
Distribution Box Input Side
Distribution Box Output Side
Jupiter Connector
200 meter long cable
Patch panel
Female Tripolar Connector
HV cable
RPC
H.V Scheme
USC
UXC

## Slide 9
H.V Distributor requirement
S.No | Components | Quantity | Status
1. | H.V cables | 360 m | Order in July
2. | Sty-cast + catalyst | Six each | Order in July
3. | Shrink wrap sleeve | 80 m | Order in July
4. | Ground cable (1.5 mm) | 160m | Order in July
Components requirement for 12 H.V distributors

## Slide 10
Wait ~ 24 hours to dry the epoxy.
Put the caps at all the 55 outputs of the distributors.
Connect the 20 input cables with the high voltage power supply.
Gradually increase the voltage with 1000V steps at 10kV and wait about 10 minutes each steps and note the current values.
If all channels remain below 0.2uA then.
Increase the volts at 11, 12, 13, 14kV for ~ 1 hour each and note current carefully it should be below 0.4uA.
H.V Dist. Testing criteria

## Slide 11
Then leave the distributor at 15kV for 12 hours at least and monitor it, the current of all channels should be less than 0.5uA
If after 12 hours all channels current remain below 0.5uA then this is a good distributor and eligible to go in the final HV system at point 5.
H.V Dist. Testing criteria

## Slide 12
H.V/L.V
Power Estimation

## Slide 13: LV cable status
For one LV analog channel, Power = V.I = 7(V) x 1.2(A)max =8.4 Watts.
Similarly, for one LV digital channel = 7.5(V) X 2(A)max = 15 Watts.
Therefore for A3009 board i.e. (6x8.4) + (6x15) = 140.4Watts.
  For one EASY Crate it will be around = 104.4 x3 = 421.2 watts.
Adding safety factor we can say total power for EASY Crate =
600 Watts approximately. (Total Power for LV = 2.4KW)
For HV system, as the current drawn is very small i.e.~15micro Ampere for applied HV ~9700V. Therefore for one HV channel the estimated power using same formula P = V.I = ~0.1455 Watt.
Power for 144 RPC’s = 144 * 0.145 = 20.882 W
  Total Power for HV = (20.882 W)
H.V/L.V Power Status

## Slide 14
For RE4 LV system, we need to route cables from USC to UXC.
    These cables are control cables and service power cables from branch controller to MAO.
There is no need to route cables from USC to UXC for HV system.
LV and HV Cables will be connected to LV and HV boards as we did for RE2 and RE3.
  These cabling schemes for RE4 HV and LV system are ready.
All the RE4 hardware will be tested in building 904 RPC test setup before installation in point 5.
Miscellaneous

## Slide 15
H.V/L.V
Grounding
Miscellaneous

## Slide 16
USC55
Cavern
Signal and I2Ccable
LV cable
HV PatchPanel
HV cables
TRIGGER CRATES
OPTICAL LINKS
HV A3512N
HV A3512N
HV A3512N
HV A3512N
HV A3512N
Easy crate (HV)‏
(A3485) AC/DC
Link Box
Easy (LV) A3016
Link Box
MAO A3486S
Link Box
Easy (LV) A3016
Link Box
MAO A3486S
Link Box
Easy (LV) A3009
Link Box
Link Box
Easy (LV) A3009
Link Box
Link Box
Easy (LV) A3009
Link Box
Link Box
Easy (LV) A3009
Link Box
48 V
10 x 4-pole shielded cable
SY 1527
Branch Control.
Branch Control.
Branch Control.
Branch Control.
Branch Control.
Branch Control.
Branch Controller
BC Control & 48 V
PatchPanel
Control shielded cable + 48 V (service)‏
SF4
HV PatchPanel
HV cables
Overall Electronics and cabling Scheme
Notes: 16

## Slide 17
FEB
FEB
FEB
To Link Board
Distribution Board
Chambers RE4/2, RE4/3 contain:
3 FEBs (each with 32 channels and 2 output cables)
1 Distrib. Board
Output connectors (each: 16 LVDS out + 4 LVDS test_in)
Input connectors (each: 16 Signal-GND pair)
Service connector:
Power Supply
I2C
Chamber Layout

## Slide 18
The FEBs are connected to input strips with coaxial cables through adapter boards
The output cables are:
  twisted flat cables inside the chambers, until the front panel
  round, shielded and twisted from front panel to Link Boards
The power cables are:
  round/shielded from LV Board (A3009) to Distribution Board
  flat cable from Distribution Board to FEBs (connected in parallel)
Chamber Layout

## Slide 19
Floating HV Power supply
Gaps
Cu Foil
Cu Foil
(signal ground)
Al chassis
FEB
DGND
AGND
Distribution Board
LV Current returns
Coax cables
HV connector
Floating LV Power supply
HV current return
(1)
(2)
Define the STAR Center on the front panel (close to HV connector)
  (1) Connect the Cu Foil (AGND) to Star Center with Cu braid
  (2) Connect the HV c.r. (from HV connect.) to Star Center with Cu braid
The Al enclosure must be tied to safety GND
  RPC is mechanically connected to Yoke (Now in mounting on post)
  Proper connection (short) from Chamber to Yoke with wide Cu braid
LV-HV-Signal-DCS shields connected to front-panel with short connections
Internal Gnd Connection

## Slide 20
Ctrl Board
HV 3-pole shielded cable
LV 8-pole shielded cable
FEB
6 x 40 poles LVDS FEB Out and Test
8 poles LVDS I2C cable (SCL, SDA)‏
YOKE (Mounting Post)
A3512N
in USC55
Tower RACK
Link Board
CAEN A3009
HV P.P.
10 x 4-pole shielded cable
Rack
earth
CAEN A3016
Link Board
FEB
FEB
D.B.
All external cables are shielded
The shields are connected (only) on the chamber frame
The far-ends are provided with ground straps, to be connected if useful
Shielding connection

## Slide 21
Thanks