## Sheet1
RE4 Component list
CONTENTS MUST BE VERIFIED BY ISR construction team
NON VERIFIED Transcription
Items | Components | Production site or | [7 empty] | Status | Comments | Comment
|  | CERN catalog SCEM number |  | Quantity for 1 chamber |  | Quantity for 10 chambers |  | Quantity for 170 chambers | Cost for 170 ch
|  |  | Reference |  | Cost for 1 ch |  | Cost for 10 ch
1 | Gas-gaps | Produced in Korea | Drawings | 3 |  | 30 | 0 |  |  | ok | In ISR | In ISR
2 | honeycomb box | Produced in China | Drawings | 1 |  | 10 | 0 |  |  | ok | In ISR | In ISR
3 | Readout strip | Produced in China | Drawings | 1 |  | 10 | 0 |  |  | ok | In ISR | In ISR
4 | Copper + mylar sheets | Produced in China | Drawings | 3 |  | 30 | 0 |  |  | ok | In ISR | In ISR
5 | Screen box | Produced in China | Drawings | 1 |  | 10 | 0 |  |  | ok | In ISR | In ISR
6 | Gas-gaps fixation L-brackets | Produced at CERN workshop | Drawings | 4 |  | 40 | 0 |  |  | 16 missing | Drawings | See Jean-Paul (Luc's drawings:
7 | Plexiglass Gas-gaps spacers (with holes) | Produced at CERN workshop | Drawings | 3 |  | 30 | 0 |  |  | 12 missing | Drawings | l-r2(3)-left-bottom.pdf,
8 | Patch panels | Produced at CERN workshop | Drawings | 2 |  | 20 | 0 |  |  | 10 missing | Drawings | l-r2(3)-left-top.pdf,
9 | insulation mylar between HCP and gas gaps | Produced at ISR | Drawings | 2 |  | 20 | 0 |  |  | 10 missing | Drawings | l-r2(3)-right-bottom.pdf,
10 | gas outlet block pipes (Which Pipe) | Silicon glue rod ? | ? | 4 |  | 40 | 0 |  |  | ok | in ISR | l-r2(3)-right-top.pdf)
[7 empty] | 0 |  |  |  |  | See Jean-Paul (Luc's drawings:
11 | Gas pipe (between gaps and from gap to patch panel) | Produced at ISR | Drawings | 6 |  | 60 | 0 |  |  | 24 missing |  | plexi-r2(3)-bottom.pdf,
12 | Cooling + FEB holding unit | Produced at CERN workshop | Drawings | 1 |  | 10 | 0 |  |  | 6 missing |  | plexi-r2(3)-mid.pdf,
plexi-r2(3)-top.pdf)
Mechanical | [11 empty] | See Jean-Paul (Luc's drawings:
accessories | [11 empty] | l-profile-r4-ring2(3).pdf
l-profile-small-ring2(3).pdf
13 | Legris ferrule unions and accessories | CERN SCEM No: | 41.34.31.656.8 | 4 |  | 40 | 0 |  |  |  | For gas pipe | Note: HV connector holding slot should be modified to 3-pin connector)
|  | CERN SCEM No: | 41.34.35.406.8 | 4 |  | 40 | 0 |  |  |  | For gas pipe
|  | CERN SCEM No: | 41.34.35.120.9 | 4 |  | 40 | 0 |  |  |  | For gas pipe
14 | Legris bulkhead unions | CERN SCEM No: | 41.34.06.510.0 | 4 |  | 40 | 0 |  |  |  | For gas pipe | (Luc's drawings:
15 | Dia 6mm LDPE gas pipe | Angst pfister ref. | A03.758241.001 FT 12 1001 0604 | 4 |  | 40 | 0 |  |  |  | For gas pipe | mylar1-r2(3).pdf,
16 | Legris ferrule unions and accessories | CERN SCEM No: | 41.34.31.658.6? | 2 |  | 20 | 0 |  |  |  | For cooling pipe | mylar5-r2(3).pdf)
|  | CERN SCEM No: | 41.34.35.408.6? | 2 |  | 20 | 0 |  |  |  | For cooling pipe
|  | CERN SCEM No: | 41.34.35.123.6? | 2 |  | 20 | 0 |  |  |  | For cooling pipe
17 | Legris bulkhead unions | CERN SCEM No: | 41.34.06.513.7? | 2 |  | 20 | 0 |  |  |  | For cooling pipe | (see item 18)
18 | Mylar sheets | CERN SCEM No: | 44.84.50.390.0 | 175?m thick,1232mm wide |  | #VALUE! | #VALUE! |  |  |  |  | In ISR
19 | M6×12 screws (Was magnetic, now amag. SS) RE4/3 | Bossard | BN 616 A2 | ~80/240 |  | #VALUE! | #VALUE! |  |  |  | conical head allen key | (Yong's drawings in
| M6×12 screws (Was magnetic, now amag. SS) RE4/2 |  | BN 616 A2 | ~70/240 |  | #VALUE! | #VALUE! |  |  |  | conical head allen key
[6 empty] | 0 | 0 |  |  |  |  | RE4_gaspipe-design.ppt)
20 | M6 washer | CERN SCEM No: | 47.78.12.060.6 | 20 |  | 200 | 0
21 | M5×6 screws | CERN SCEM No: | 47.62.71.200.9 | 30 |  | 300 | 0
22 | M5 washer | CERN SCEM No: | 47.78.12.050.8 | 20 |  | 200 | 0
23 | M3×16 screws | CERN SCEM No: | 47.62.32.316.4 | 12 |  | 120 | 0
24 | M3 nuts | CERN SCEM No: | 47.41.65.030.8 | 12 |  | 120 | 0
25 | M3 washer | CERN SCEM No: | 47.78.12.030.2 | 12 |  | 120 | 0
26 | M3×4 screws | CERN SCEM No: |  | 12 |  | 120 | 0
27 | M3×8 plastic screws | CERN SCEM No: |  | 12 |  | 120 | 0
28 | M3.2×3mm plastic washers | CERN SCEM No: | Not a metric ISO | 12 |  | 120 | 0
Electronics components
29 | FEBs | Made in Pakistan |  | 3 |  | 30 |  |  |  |  | Order?
30 | FEB insulation mylars | Produced at ISR | Drawings | 3 |  | 30 |  |  |  |  | Put between FE board and copper supporting plate, produced in ISR
31 | distribution board | Made in Pakistan |  | 1 |  | 10 |  |  |  |  | Order?
32 | 3 pin HV connector | CPE | 28-019r05 | 1 |  | 10 |  |  |  |  | In ISR
33 | STYCAST glue 2651-40/Catalyst | Abovo AG (CH) | EDH | ?g/connecctor |  | #VALUE! |  |  |  |  | To make HV connector (ratio: 100:18)
34 | Copper screen braids for HV | CERN SCEM No: | 04.01.31.006.7 | 5 |  | 50 |  |  |  |  | In ISR
| and ground wires | CERN SCEM No: |  |  |  | 0
0
35 | Heat shrinkable tube (4.8/2.4mm) | CERN SCEM No: | 04.86.62.110.3 (d3mm) | 1 |  | 10 |  |  |  |  | Used for ?
| ?? | CERN SCEM No: | 04.86.62.110.5 (d5mm) | 2 |  | 20
36 | ground wires (Red, W,B,G) there are 5 wires and HV shield | CERN SCEM No: |  | 6 |  | 60
37 | Signal flat cable with two connectors |  | Produced at ISR | 1 |  | 10 |  |  |  |  | See item 41,42,43,44,45
38 | FEB LV cable with 4 connectors |  | Produced at ISR | 6 |  | 60 |  |  |  |  | See item 40,46,47
39 | Adopter soldered with 16 co-ax wires with ferrules mounted |  | Produced at ISR? | 2m |  | #VALUE! |  |  |  |  | See item 48,49,50
40 | 26 pin twisted pair flat cable | CERN SCEM No: | 04.21.22.426.8 | 10m |  | #VALUE! |  |  |  |  | For LV power
41 | 40 pin twisted pair flat cable | CERN SCEM No: | 04.21.22.440.0 | 6 |  | 60 |  |  |  |  | For FEB signal
42 | 40 pin socket flat cable connector | CERN SCEM No: | 09.55.03.340.4 | 6 |  | 60 |  |  |  |  | FEB end
43 | 40 pin socket flat cable connector | CERN SCEM No: | 09.55.03.440.1 | 6 |  | 60 |  |  |  |  | Anti-traction loop for female cable socket (FEB end)
44 | 40 pin plug flat cable connector | CERN SCEM No: | 09.55.04.540.4 | 6 |  | 60 |  |  |  |  | Male cable plug with securing feet (patch panel end)
45 | 40 pin plug flat cable connector | CERN SCEM No: | 09.55.04.740.8 | 6 |  | 60 |  |  |  |  | Anti-traction loop (patch panel end)
46 | 26 pin socket flat cable connector | CERN SCEM No: | 09.55.03.326.2? | 4 |  | 40 |  |  |  |  | Connecting FEBs
47 | 26 pin socket flat cable connector | CERN SCEM No: | 09.55.03.426.9? | 4 |  | 40 |  |  |  |  | Anti-traction loop for female cable socket (Connecting FEBs)
0
0
48 | Coax cable DRAKA (CA50-2-1 0.5L/1.5-LSHF) strv | CERN SCEM No: | 04.61.11.110.6?04.61.11.145.5 | 80 | 43.2 | 800 |  |  |  |  | Coax cable C-50-1-2 50 Ohm ACI
49 | Adapter board | Pakistan |  | 6 |  | 60 |  |  |  |  | See Ian
50 | ferrules 09.46.11.195.9 (Adapter End) | From Company |  | 96 | 136 | 960 |  |  |  |  | See Ian
50.1 | ferrules , round (Cu,Sn) material (Copper sheet End) | From Company |  | 96 |  | 960
Tooling & Materials
51 | 6 soldering protection strips | Made in ISR | Cu & MylaR 200microns |  |  | 0 |  |  |  |  | Copper glued to thick mylar strips
52 | Pipe heat bending tools | Made by Jean-Paul | drawings |  |  | 0 |  |  |  |  | In ISR
53 | Loctite 245 glue (blue) | CERN SCEM No: | 37.30.35.074.3? |  |  | 0 |  |  |  |  | Fix gas unions on patch panel
54 | Soldering tin (Pb62% Sn36% Ag2%) | CERN SCEM No: | 29.20.01.362.9 |  |  | 0 |  |  |  |  | Tin-lead-silver wire of welding for electronics
55 | Conductive copper tape | CERN SCEM No: | 04.95.20.112.8 |  |  | 0 |  |  |  |  | Seal copper ground (not needed if using solder)
56 | Conductive Aluminum tape | CERN SCEM No: | 04.95.20.150.9 |  |  | 0 |  |  |  |  | Seal screen box
57 | Plastic insulation tape | CERN SCEM No: | 04.94.20.213.0 |  |  | 0 |  |  |  |  | Cover slots in honeycomb panel, L fixation brackets, HV slots etc.
|  | CERN SCEM No: | 04.94.20.225.6 |  |  | 0
58 | Paper tape | CERN SCEM No: | 04.95.45.225.0 |  |  | 0 |  |  |  |  | Low adhesive
|  | CERN SCEM No: | 04.95.45.251.8 |  |  | 0
59 | Cleaning paper | CERN SCEM No: | 55.60.82.150.2 |  |  | 0 |  |  |  |  | In ISR
60 | Cleaning solution ? | CERN SCEM No: | ? |  |  | 0
Transcribed by I. Crotty
2011-04-20
Input from Waqar & Ian 27 may 2011