## List
Laboratory equipment list
CONTENTS MUST BE VERIFIED BY assembling sites
Mumbai : 3 rpcs in the cosmic stand , 3 gaps with standard rpc mixture , 3 gaps with argon, 8 gas ch with stand mixt. + 3 Ar
max. flow : 5 lit/hour
Ghent : 5 RPCS in the cosmic stand, 5 gaps, 12 gas channels standard , Argon line is present , 5 gas channels for Argon + 1line for leak test (separate Bot.)
Cern : 6(10) RPCSs, 10 gaps, 12 channels standard mixture, 12 gas channel for Argon + 1line for the leak test (separate Bot)\
3gaps
23 HV channels, 5 LV channels / site
Items | Components | Responsibility | Quantity needed (Ghent) | Quantity needed (India) | Quantity needed (CERN) | Item cost | Quantity for the 3 sites | spares | Total | ITEM | SUPPLIER | STATUS
Read-out :
1 | 8 Ch - Frequency-meter with signal cable and power adaptor | Napoli | 1 | 1 | 1 | <500 euros | 3 | 1 | 4 | Connectivity & threshold scan | University of Napoli | Will be delivered begin november
2 | I2C Nim module | Bari | 1 (+1) | 1 | 1 |  | 3 | 1 | 4 | Thesholds |  | 1(old in ISR)+2(gent)+1(cern)+1(India)
7 | NIM Blue module (LVDS-->NIM) | Bari | 1 | 1 | 1 |  | 3 | - | 3 | easy monitoring of the signals from the strips |  | avalaible 3
9 | signal cables (TDC-chamber) | Gent | 15 +3 | 9+7 | 30 +5 |  |  |  | 69 | Mumbai :0k, gent : No, Cern:Ok
| Chamber & Gap powering: | [10 empty] | Gent: OK, CERN : Nicolas+Andrey, India : one missing
10 | SY1527 HV Frame | sites | 1 | 1 (2527 for HV) + 1 (for LV) | 2 |  | 3 |  | 3 |  |  | Mumbai : ok, 1 (Ghent) +1 (904) +1 (ISR)
11 | A1526N (HV) | sites | 4 | 4 | 7 |  | 12 |  |  |  |  | Gent: OK, CERN : Nicolas+Andrey, India : one missing
12 | HV cables (jupiter (F) -jupiter(F)) | CERN | 25 | 24 | 40 |  | 75 |  |  | lengths=?
13 | A1513A (LV) | sites | 3 | 2 | 5 |  | 6 |  |  |  |  | avalaible Ghent : 3, Mumbay: 2, Cern :5
14 | LV cable subD37pin - 2 x Molex | Mumbai | 3 | 2 | 5 |  | 10 | 3 | 13
Gas leak and spacer test:
16 | High Resolution Picco Data Logger ADC-20/ADC-24 | commercial | 1 | 1 | 1 | 1 | 3 | 1 | 4 |  |  | 3 delivered at cern , 1 delivered at Gent
18 | Pressure SENSOR CTE7000 0 +40 MBAR | cern | 1 |  |  |  | 3 |  |  |  |  | 3 delivered at cern , 1 delivered at Gent, 1 installed at cern
| Adapter board to ADC |  | 1 | 1 | 1 | 1 | 3 | - | 3 |  |  | 3 boxes delivered at cernby gent +1 card, , gent:ok
1 | Power supply for the ADC : 15V & I >15mA | sites | 1 | 1 | 1 |  | 3 |  | 3 |  |  | 1 PS avalaible in ISR
Cosmic stand
20 | NIM crates (trigger) | sites | 1 | 1 | 2 |  | 12 |  | 12 |  |  | OK
| NIM crate (DAQ) | sites | 1 | 1 | 1 |  | 3 |  | 3 |  |  | OK
21 | VME crate (Daq) | sites | 1 | 1 | 1 |  | 3 |  | 3 |  |  | OK
22 | scalers (Trigger) |  | 3 | 2 +1 | 3 |  | 12 |  | 12 | monitore the noise and rates |  | gent: OK, Mumbai OK (need 1 more from EEP), CERN :
23 | Coincidence units |  | 4 | 4 | 4 |  | 12 |  | 12 | provide trigger |  | gent: OK, Mumbai OK, CERN : OK
24 | Discriminators unit |  | 10 | 10 | 10 |  | 30 |  | 30 | Thresholds for the PMs |  | OK
25 | Analog Fan in Fan out units |  | 10 | 10 | 10 |  | 30 |  | 30 | split signals from the PMs (trigger I/O register) |  | gent: OK, Mumbai 10 from Pool , CERN : OK
| Logic Fan in Fan out |  | 2 | 2 | 4 | [6 empty] | Gent : OK, Mumbai no, CERN:OK
| FAST OR modules |  | 4 | 5 | 5 |  | 12 |  | 12 |  |  | gent : Ok, Mumbai verify if 8 channels, CERN OK
26 | Dual Timer |  | 2 | 2 | 2 |  | 9 |  | 9 | delay for the common stop and fake triggers generation |  | gent : Ok, Mumbai no, CERN OK
| NIM<-->LVDS module (RPC receiver) |  | 1 | 1 | 1 | [6 empty] | Gent : ok, Mumbai :ok Cern :ok
| NIM-ECL-NIM (lecroy) |  | 2 | 2 | 4
27 | Delay units : |  | Total =>500ns - 1uSec | yes | yes | [6 empty] | OK
28 | VME I/O registers : |  | 1 | 1 | 1 |  |  |  |  | Identifing which hodoscope has been triggered |  | Gent:OK, Mumbai:, cern:OK
29 | VME crate controller …. |  | 1 | 1 | 1
2 | V1190A - 128 Ch. Multievent Multihit TDC | CERN | 4+1 | 2+1 | 8+? |  | 14 | 2+? | 16+? | record data from the chambers |  | delivered at CERN 04/5/2011 (6 cern+2 gent), 3 will be delivered in Mumai in o1/2012
| V1290A 32 channel TDC | Mumbay | 3 | [5 empty] | 3
| V2718 caen with optical link (DAQ controller) |  | 1 (differ. In gent) | 1 | 1 | [6 empty] | OK
| special TDC connector Adaptor | CERN/CAEN ?
30 | Lemo cables and adaptors
| Pulse generator 25 ns clock to the TDCs ? |  | 1 | 1 | 1 | [6 empty] | ?
TTL to NIM adaptor
Instruments :
31 | Oscilloscope |  | 1
| Multimeter |  | 2 |  |  |  | 6 |  | 6 | adjust hardware thresholds
Cooling tests:
Environmetal parameters :
| Oregon scientific meteo station WMR 200 | Gent | 1 | 1 | 1 |  | 3 | 1 | 4 | Gent :WMR200 Ok, India : WMR200, cern : WMR-968 ok
| T-Humidity & pressure sensors | Gent | 1 |  |  |  | 3 | 1 | 4 | env. Conditions
| PICO (T and Humidity for gas) | Gent | 1 | 1 | 1 |  | 3 | 1 | 4 | gas conditions
Software:
| Software controlling the HV main Frame : HV scan + HV long term + Ar scan | Ghent | [9 empty] | done Tome Thesis
| LabView version 7 or latest? | Commercial |  | version 8.5
| I2C Software | Bari | [9 empty] | To check if is it working under LabViewV10
| Software reading the meteo station under Linux | Ghent
| DAQ - Online | each site
| DAQ - Analysis | common
DataBase
Gas Lines :
| Argon | sites | yes | yes | yes
| SF6 | sites | yes | yes | yes
| Freon | sites | yes | yes | yes
| Isobutane | sites | yes | yes | yes
| Humidifies | sites | yes | yes | yes
| 10-ch Gas Rack for standard and/or Argon mixture | sites | ready | ready | under construction
| gas rack for spacer and leak test | sites | ready | not yet ready | ready (ISR)
| separate Ar line | sites | yes | yes | under construction

## xxxx
CERN cosmic stand
15 PMTs | 20 ordered | HAMAMATSU H11xxx | Archana
CAEN TDC V1190A | 128
All the signal cables should have the same length
TDC - 40 pin Adaptor | under stady to be produced at cern
Ghent
TDCS 4 +1 modules | 8 arrived at cern --> 5 units for Gent
5 slots | 5x96=480 channels
HV modules : 2
WV1190AEXAAA V1190A - 128 Ch. Multievent Multihit TDC
ordered 8 in total, delivered 8
India
6 slots
16-18 scintillators | x 2 PMTs/scintialltor
mechanical assembly of a chamber: 2days ( 1 day when experienced)
Leak test : 3 gaps /working day | then during night Argon --> morning HV aArgon
| then night normal mixture then next day HV scan | 2
Total for 3 gaps : 3 days
QC gaps | 3 slots for ghent and India, 6 slots for CERN
group of 10 (ghent=5,india=6) during 5 days in the cosmic stand
1days x 10 +5 =15 days for the whole QC

## Blue module
Description | QTY | SCEM | Documentation | status
NIM Blue module (LVDS-->NIM) | 1 | Bari home made | I50 pins output connector:contains 2x16 inputs from FEB and 2x4 outputs to FEB (Test pulses). | 3 delivered at cern
40 pin Twisted pair cable
40 pinFemale cable socke (1) | 1 | 09.55.03.340.4
40 pinFemale cable socke (2) | 1 | 09.55.03.440.1
50 pinFemale cable socke (1) | 1 | 09.55.03.350.2
50 pinFemale cable socke (2) | 1 | 09.55.03.450.9

## signal-cable
Description | QTY | SCEM | Documentation | Gent |  | Mumbay |  | CERN |  | Total | status | To order 18Oct2011
|  |  |  | details | total | details | total | details | total
connector FERNELL in ONE (TDC) | 1 |  | DAI 4751701 | [6 empty] | 85 | 40 | 50
3m male 2x17 pin connector chassis | 2 | 09.55.04.534.2 |  |  | 40 | Done |  |  | 40 | 100 | 0 | 100
3m male 2x17 pin connector clamp | 2 | 09.55.04.734.6 | ???? |  | 40 | Done |  |  | 40 | 100 | 0 | 100
3m female 2x17 pin connector Socket | 2 | 09.55.03.334.2 |  |  | 40 | Done |  |  | 40 | 100 | 0 | 100
3m female 2x17 pin connector Socket Clamp | 2 | 09.55.03.434.9 |  |  | 40 | Done |  |  | 40 | 100 | 0 | 100
34 pin twisted pair cable | 2 | use old (ISR) | ????
34 pin twisted pair cable | 2 | 04.21.22.434.8 |  | 20 x 0.5 = 25m ! | 25 | Done |  | 20 x 0.5 = 25m ! | 25
34 pin twisted pair cable | 2 | 04.21.22.434.8 |  | 10 X (30+6) = 360m | 360 | 5 x (18 +6) = 120m | 120 | 12x (60 + 12) = 864m | 864 | 1410 |  | 1410m
3m female 2x20 pin connector Socket | 2 | 09.55.03.340.4 |  |  | 36 |  | 24 |  | 72 | 150 |  | 150
3m female 2x20 pin connector Socket Clamp | 2 | 09.55.03.440.1 |  |  | 36 |  | 24 |  | 72 | 150 |  | 150
1 TDC=4 conectors ==> 4 x 2 16 pairsconnectors
Additions made by:
Pino, Lalit,Salvatore, Ian as dicussed with Nicolas 18 Oct 2011
40c cable changed to 34 by Lalit and Ian. Requires approval. 24 oct 2011

## LV-cable
Description | QTY | SCEM | Documentation | Gent | Mumbay | CERN | status
LV cable 8 x 0.75 wires (blue) | 1 |  |  | 10m | 7m | 5m ? | 100m
connector sub DB37 male | 2 | 09.21.20.714.4
capot 1 | 2 | 09.21.23.016.3
heat shrink Atum 12/4-0 | 0.015 | Raytronics CH-6331 | EDH 4614881 |  |  |  | 30m
shield braid | 2m | 04.01.33.050.5 |  |  |  |  | 100m
Poly braid to cover wires | 2m Æ10 | 04.86.45.028.4
earth lug | 4 | 04.76.26.424.9 | ? |  |  |  | 200
earth cable | 1m | 04.01.61.640.2 |  |  |  |  | 20
molex | 2 | Radiospares 2332775 | EDH 4758752
molex pins | 8 | RADIOSPARES 2333009 | EDH 4758752

## Frequencym
|  | quantity | scem
connector | 2x20 c | 1 | 09.55.03.340.4
connector | 2x20 c | 1 | 09.55.03.440.1
connector | 2x8 | 2 | 09.55.03.316.4
connector | 2x8 | 2 | 09.55.03.416.1
connector | 2x10 c | 1 | 09.55.03.320.8
connector | 2x10 c | 1 | 09.55.03.420.5
flat cable | 2x20 c | 1.5m | 04.21.22.440.0
power supply | 12 V 300mA | 1 | jumbo
RPC-CMS 8ch freq. meter |  | 1 | University of Napoli

## I2c module
|  | QTY | SCEM | Documentation | Gent | Mumbay | CERN
RS232 cable for the I2C module | sub-D 9 femelle - sub-D 9femelle | 1 |  |  | 4m ? | 4m ? | 4m ?
RS232/USB adaptor | Sub-D 9 Mâle à USB B Femelle | 1 | 80.02.09.001.9
usb cable | male - male |  |  |  | ? | ? | ?
34 pin Twisted pair cable for the I2C module |  |  |  |  | 5m ? | 5m | 5m
3m IDC-female connector | 2x34 pins | 1 | 09.55.03.334.2
3m IDC-female connector | 2x34 pins | 1 | 09.55.03.434.9
3m IDC-female connector | 2x5 pins | 5 | 09.55.03.310.0
3m IDC-female connector | 2x5 pins | 5 | 09.55.03.410.7

## HV-cable
Description | QTY | SCEM | Documentation | Gent | Mumbay | CERN | status
HV - single coax 15 KV RG58 |  | PREV 3864L-ZH | ( supplier CPE) | 10 m (cosmic) , 13m (gaps) | 15m | ? | 100 m (ISR)
Jupiter cable Connector HV | 2 | 23.100.052-045 | (supplier CPE) |  |  |  | 20
Female pin | 2 | 533-F3 | (supplier CPE) |  |  |  | 200
Insulator Mal HV | 2 | 533-F4 | (supplier CPE) |  |  |  | 50
Metal cyl.for red cable | 2 |  | (supplier CPE) |  |  |  | >150
heat shrink Atum 12/4-0 | 0.015 | Raytronics CH-6331 | EDH 4614881

## Adapter Board
Description | QTY | SCEM | Documentation | Gent | Mumbay | CERN | status
2 wires white cable | 1 | 04.21.51.055.4
connector for pressure sensor | 1 | ELWIKA 4012 PG 9
Farnell ADC-20/ADC-24 Terminal Board | 1