## List
Cables for RE4 UXC & USC
|  | Ian Crotty | 2011-11-23
Total Material costs
Chamber cables
Signal cable chamber to LBB | 6056.2
DCS cable chamber to LBB | 454.62
HV cables chamber to YE1PP
LV cables chamber to Caen 3009
3 Phase cable rear rack
48V ACDC to Easy
Branch Controller
48V service Power
48V service Power
Communication BC to UXC
Communication YE1PP to ACDC
Trigger cables
LV 3016 to LBB
Ethernet "Ring"
Fibres
Signal from LBB to UXC
LBB to YE1 PP
TTC
Comm ACDC to Easy Crate

## Signal ch to LBB
Signal Cable to LBB
|  | Ref or SCEM | Unit cost [chf] | Required | Units | to order | Tot cost | Order Ref | Delivered | Missing
[chf]
Cable ref | BLINDE 40xAWG28
| 23100 | 04.71.06.400.0 | 3.6 | 9493 | [m] | -13610 | 0 |  |  | ISR
Connectors | 40 pin
Scem | 3M IDC | 09.55.03.340.4 | 1.95 | 1728 | piece | 1900 | 3705 | 4952989 |  | X
| IDC clamp | 09.55.03.440.1 | 0.22 | 1728 | piece | 1900 | 418 | 4952989 |  | X
| Heat shrink dia12mm L=60mm | 04.86.62.130.9 | 3 | 105 | [m] | 120 | 360 | 4952989 |  | X
| Heat shrink dia 10mm L=30mm | **Atum-12/4-0-stk | 8.55 | 52 | [m] | 60 | 513 |  |  | X
| PA sheath dia 10mm L= 500mm | 04.86.45.028.4 | 0.76 | 864 | [m] | 950 | 722 | 4952989 |  | X
| ground connection 0.5mm2 | 04.01.61.640.2 | 0.39 | 518 | [m] | 570 | 222.3 | 4952989 |  | X
| ground lug | 04.76.22.306.0 | 0.061 | 1728 | piece | 1900 | 115.9 | 4952989 |  | X
| Labels | [8 empty] | X
| packing Protection | [8 empty] | X
| Cable ties | [8 empty] | X
TOTAL Cost [chf] | [6 empty] | 6056.2
** https://edh.cern.ch/Document/SupplyChain/DAI/4772929
[6 empty] | Ian Crotty |  | 2012-04-23

## DCS ch to LBB
DCS Cable to LBB
|  |  | Unit cost [chf] | Required |  | to order | Tot cost | Order Ref | Delivered | Missing
|  | Ref or SCEM |  |  | Units |  | [chf]
Cable ref | BLINDE 2x4xAWG28 | 04.21.70.103.0 | 0.38 | 1600 ?? | [m] | In the ISR | 0 |  |  | ISR
| Cat 5 LAN |  |  | 144 | piece | 160
Connectors
Scem | 3M IDC 10 pin | 09.55.03.310.0 | 0.88 | 288 | piece | 320 | 281.6 |  |  | X
| clamp | 09.55.03.410.7 | 0.24 | 288 | piece | 320 | 76.8 |  |  | X
| Heat shrink dia 9.5mm | 04.86.62.120.1 | 2.6 | 8.64 | [m] | 10 | 26 |  |  | X
| ground connection 0.5mm2 | 04.01.61.640.2 | 0.39 | 115.2 | [m] | 130 | 50.7 |  |  | X
| ground lug | 04.76.22.306.0 | 0.061 | 288 | piece | 320 | 19.52 |  |  | X
TOTAL Cost [chf] | [6 empty] | 454.62
Ian Crotty
25.07.2012

## HVch to YE1
HV Cable chamber to YE1 PP
|  | Ref or SCEM | Quantity/cable | Unit cost [chf] | Required | Units | to order | Tot cost | Order Ref | Delivered | Missing
cable quantity | In stock [m] | [6 empty] | [chf]
| 3110 | 1×(2×0.22+2×0.22)H2M1 15KV |  | 1 | 2009 | [m] | -1100 |  |  |  | ISR
Cable ref
[5 empty] | 144 | piece | 160 |  |  |  | X
Connectors
| CPE | CPE 28.002.512.020 | 2 | 26 | 288 | piece | 320 | 8320 | 4903205 |  | X | 4898223
| *STYCAST glue 2651-40 | Abovo AG (CH) | 0.05 | 146 | 7.2 | [kg] | 10 | 1460 | 4971709 |  | X
| Stycast Catalyser | LV23 catalyser | 0 | 0 | 0 |  | 0 | 0 | 4971709 |  | X
| Heat shrink dia 18-6mm | Atum-18/6-0-stk | 0.2 | 12 | 28.8 | [m] | 30 | 360 | 4972890 |  | X
| Heat shrink dia 9-3mm | **Atum-9/3-0-stk | 0.1 | 8.55 | 14.4 | [m] | 20 | 171 | 4972890 |  | X
| Heat shrink dia 8-4mm | Raychem 04 86 62 120.1 | 0.1 |  | 14.4 |  | 20
| ground connection 0.5mm2 | 04.01.61.640.2 | 0.6 | 0.39 | 86.4 | [m] | 100 | 39 |  |  | X
| ground lug | 04.76.22.306.0 | 2 | 0.061 | 288 | piece | 320 | 19.52 |  |  | X
| Paper tape 20mm | 04.95.45.225.0 | 1 | 0.044 | 144 | piece | 160 | 7.04 |  |  | X
| labels |  | 2 | [7 empty] | X
| packing Protection |  | 1 | [7 empty] | X
| Cable ties |  | 2 | [7 empty] | X
TOTAL Cost [chf] | [7 empty] | 10369.52
Total less the Hv Connector See EDH 4903205 | [7 empty] | 2049.52
| *Abovo AG (CH) | voir EDH 4586561
** https://edh.cern.ch/Document/SupplyChain/DAI/4772929
Coaxial cabel oredered 4799645
Heat Shrink 12/4 ordered 4772929
Stycast ordered 4772884
| Updated | 2013-03-25 | heat shrink add & mod.

## LV ch to 3009
LV
LV Chambre to 3009
|  |  | Supplier Ref. | Manufacture Ref. | Quantity/cable | Unit cost [chf] | Required | Units | to order | Tot cost | Order Ref | Delivered | Missing
| cable quantity | In stock | Ref or SCEM |  |  |  | [m] | [m] |  | [chf]
| Cable ref | BL | LV Cable 8x0.75FMOH2M1-300 |  |  |  | 1600 ?? |  | ??? | ?? |  |  | X
[7 empty] | 144 | piece | 160 |  |  |  | X
| Connectors | Molex
|  | Molex(RadioSpares) | 233-2775 | 43025-0800 | 2 | 0.98 | 144 | piece | 160 | 156.8 |  |  | X
|  | Pins (RadioSpares) | 233-3009 | 43030-0007 | 8 | 0.082 | 576 | piece | 630 | 51.66 |  |  | X
|  | ***Power Pole | 1327-BK Red |  | 2 | 0.5 | 144 | piece | 160 | 80 | 4989817 |  | X
|  |  | 1327G06 Black |  | 2 | 0.5 | 144 | piece | 160 | 80 | 4989817 |  | X
|  |  | 269G2-LPBK |  | 4 | 1.2 | 288 | piece | 320 | 384 | 4989817 |  | X
|  | Heat shrink dia 12-4mm | **Atum-12/4-0-stk |  | 0.5 | 8.55 | 36 | [m] | 40 | 342 | 4955533 |  | X | 4994347 ?
|  | sheath (PolyBraid) | 04.86.45.024.8 |  | 3.5 | 0.57 | 252 | [m] | 280 | 159.6 | 4985695 |  | X
|  | shield braid | 04.01.33.050.5 |  | 3.5 | 1.8 | 252 | [m] | 280 | 504 | 4985695 |  | X
|  | ground connect. 0.5mm | 04.01.61.640.2 |  | 1 | 0.39 | 72 | [m] | 80 | 31.2 | 4985695 |  | X
|  | ground lug dia6mm | 04.76.22.306.0 |  | 4 | 0.062 | 288 | piece | 320 | 19.84 | 4985695 |  | X
| TOTAL Cost [chf] | [8 empty] | 1809.1
https://edh.cern.ch/Document/SupplyChain/DAI/1750277
https://edh.cern.ch/Document/SupplyChain/DAI/1808493
https://edh.cern.ch/Document/SupplyChain/DAI/2118247
** https://edh.cern.ch/Document/SupplyChain/DAI/4772929
***http://www.rotima.ch/
http://www.newark.com/anderson-power-products/1327/plug-socket-connector-housing/dp/29C5329?whydiditmatch=rel_1&matchedProduct=90B1226

## 48V ACDC to Easy
48V ACDC to Easy
|  |  | Unit cost [chf] | Required |  | to order | Tot cost | Order Ref | Delivered | Missing
cable quantity | In stock | Ref or SCEM |  | [m] | Units |  | [chf]
Cable ref | BL | 04.71.06.XXX.x |  | XX | [m] | ??? | ?? |  |  | X
|  |  |  | XX | piece | #VALUE! |  |  |  | X
Connectors | XX pin
Scem | 3M IDC | 09.55.03.XXX |  | XX | piece | #VALUE! | #VALUE! |  |  | X
|  | 09.55.03.XXX |  | XX | piece | #VALUE! | #VALUE! |  |  | X
| Heat shrink |  |  |  | [m] |  |  |  |  | X
| sheath |  |  |  | [m] |  |  |  |  | X
| shield sheath |  |  |  | [m] |  |  |  |  | X
| ground connection |  |  |  | [m] |  |  |  |  | X
| ground lug |  |  | XX | piece | #VALUE! | #VALUE! |  |  | X
TOTAL Cost [chf] | [6 empty] | #VALUE!

## Comm ACDC to EASY
Communication ACDC to Easy Crate
|  |  | Unit cost [chf] | Required |  | to order | Tot cost | Order Ref | Delivered | Missing
cable quantity | In stock | Ref or SCEM |  | [m] | Units |  | [chf]
Cable ref | BL | 04.71.06.XXX.x |  | XX | [m] | ??? | ?? |  |  | X
|  |  |  | XX | piece | #VALUE! |  |  |  | X
Connectors | XX pin
Scem | 3M IDC | 09.55.03.XXX |  | XX | piece | #VALUE! | #VALUE! |  |  | X
|  | 09.55.03.XXX |  | XX | piece | #VALUE! | #VALUE! |  |  | X
| Heat shrink |  |  |  | [m] |  |  |  |  | X
| sheath |  |  |  | [m] |  |  |  |  | X
| shield sheath |  |  |  | [m] |  |  |  |  | X
| ground connection |  |  |  | [m] |  |  |  |  | X
| ground lug |  |  | XX | piece | #VALUE! | #VALUE! |  |  | X