## Sheet1
Cable up-date
| Components list | Cable lengths Walter | Cable lengths 3D Model | componets at CERN | contract to produce | Connectors transported to producer | Labels Printed | prototype done | delivery schedule | First delivery | Second delivery | Third delivery
Cable type
Signal | 2012 | 2012 | 2013-01-01 | 2012 | 2013-01-01 | 2013-01-01 | 2013-01-01 | Fev 2013 | 2 months | x12 (Fev2013)
DCS | 2012 | 2012 | fev 2013 | 2012 | 2013-01-01 | 2013-01-01 | 2013-01-01 | Fev 2013 | 2 weeks | x2 (Fev2013)
LV | 2012 | 2012 |  | 2012 | no | no | no | fev 2013 | ?
Hv | 2012 | 2012 |  | 2012 | 2013-01-01 | no | no | no | 1 month
|  |  |  | Ian Crotty |  | 2013-02-05